## legend
Story Points | Meaning | Typical Characteristics
1 | Very Small | Simple configuration, minor text change, almost no risk.
2 | Small | Straightforward change requiring little testing.
3 | Small to Medium | Simple development with a few components and low risk.
5 | Medium | Requires development, testing, and integration across multiple components.
8 | Large | Complex feature with multiple dependencies, higher uncertainty, or performance considerations.
13 | Very Large | Significant feature that should probably be split into smaller stories.
21+ | Epic | Too large for one sprint; needs to be broken down.

## coverage_survey
Demography
ID | Task | User Story | DAX Formula | Acceptance Criteria | Story Points | Priority | Owner | Status
DEMO-01 | Total Households Covered | As a programme manager, I want to view the Total Households Covered so that I can monitor the total number of survey submissions. | Total Submission = CALCULATE( COUNTROWS('COVERAGE_'), 'COVERAGE_'[I have been informed about SARMAAN in a language I understand. The research lead has discussed with me and I understand that my child participation is voluntary. I therefore agree to participate.]= "Yes" ) | • Counts all records after phase filter is applied.• Updates dynamically when filters change.• Displayed as KPI card. | 2 | High | Faiza Mukhtar | Not Started
DEMO-02 | Total Children Less Than 18 Years | As a programme manager, I want to view the Total Children Less Than 18 Years so that I can monitor the number of children captured in the survey. | How many children currently live in your household? | • Counts all records where age is less than 18 years.• Updates dynamically with filters.• Displayed as KPI card. | 3 | High | Faiza Mukhtar | Not Started
DEMO-03 | Eligible Children (1-59 Months) | As a programme manager, I want to view the number of Eligible Children aged 1-59 months so that I can monitor the target population for AZM administration. | total_eligible | • Counts children within the 1-59 month age range.• Updates dynamically with filters.• Displayed as KPI card. | 3 | High | Faiza Mukhtar | Not Started
DEMO-04 | Children Offered AZM | As a programme manager, I want to view the number of Children Offered AZM so that I can monitor coverage of drug administration. | Child Offered AZM = CALCULATE( COUNTROWS('child_eligible_'), 'child_eligible_'[Q90. Did someone offer child ${child_idd} azithromycin between 21st and 27th of November 2025?] = "Yes" ) | • Counts children marked as offered AZM.• Updates dynamically with filters.• Displayed as KPI card. | 2 | High | Faiza Mukhtar | Not Started
DEMO-05 | Children Not Offered AZM | As a programme manager, I want to view the number of Children Not Offered AZM so that I can identify gaps in AZM coverage. | Child Not Offered AZM = CALCULATE( COUNTROWS('child_eligible_'), 'child_eligible_'[Q90. Did someone offer child ${child_idd} azithromycin between 21st and 27th of November 2025?] = "No" ) | • Counts children marked as not offered AZM.• Updates dynamically with filters.• Displayed as KPI card. | 2 | High | Faiza Mukhtar | Not Started
DEMO-06 | Children Who Swallowed AZM | As a programme manager, I want to view the number of Children Who Swallowed AZM so that I can monitor compliance and effective drug administration. | Child Swallowed AZM Offered_ = CALCULATE( COUNTROWS('child_eligible_'), 'child_eligible_'[Q94. Did child ${child_idd} swallow the AZM offered?] = "Yes" ) | • Counts children marked as swallowed AZM.• Updates dynamically with filters.• Displayed as KPI card. | 2 | High | Faiza Mukhtar | Not Started
DEMO-07 | Vaccination Cards Available | As a programme manager, I want to view the Number of Vaccination Cards Available so that I can monitor documentation completeness during the survey. | HasVaccinationCard = COUNTROWS ( FILTER ( 'child_eligible_', 'child_eligible_'[Do you have a vaccination card?] = "Yes" ) ) | • Counts records where a vaccination card was seen/available.• Updates dynamically with filters.• Displayed as KPI card. | 2 | High | Faiza Mukhtar | Not Started
DEMO-08 | Total LGAs Reached | As a programme manager, I want to view the Number of LGAs Reached so that I know the geographic coverage of the survey. | A unique count of the "Q2. Local Government Area" column | • Counts unique LGAs.• Respects applied filters.• Displayed as KPI card. | 2 | High | Faiza Mukhtar | Not Started
DEMO-09 | Total Wards Reached | As a programme manager, I want to view the Number of Wards Reached so that I know the ward-level coverage of the survey. | A unique count of the "Q3.Ward" column | • Counts unique wards.• Respects applied filters.• Displayed as KPI card. | 2 | High | Faiza Mukhtar | Not Started
DEMO-10 | Total Communities Reached | As a programme manager, I want to view the Number of Communities Reached so that I know how many communities have been covered. | A unique count of the "Q4. Community Name" column | • Counts unique communities/settlements.• Respects applied filters.• Displayed as KPI card. | 2 | High | Faiza Mukhtar | Not Started
DEMO-11 | Households Visited per Implementation Day | As a programme manager, I want to view Total Households Visited per Implementation Day so that I can monitor daily collection trends. | With "_submission_time" as the category and the count of "_uuid" on the Y-axis | • Groups submissions by implementation day.• Displays chart (bar/line).• Updates dynamically with filters. | 3 | High | Faiza Mukhtar | Not Started
DEMO-12 | Submissions per Research Assistant | As a programme manager, I want to view the Total Number of Submissions per Research Assistant so that I can monitor individual field staff performance. | With "Q2. Local Government Area" and "confirm user and phone number" on the X-axis and "Total Submission = CALCULATE( COUNTROWS('COVERAGE_'), 'COVERAGE_'[I have been informed about SARMAAN in a language I understand. The research lead has discussed with me and I understand that my child participation is voluntary. I therefore agree to participate.]= "Yes" )" on the Y-axis | • Groups submissions by Research Assistant.• Sorts descending by count.• Updates dynamically with filters. | 3 | High | Faiza Mukhtar | Not Started
DEMO-13 | Visitation by CDD for MDA | As a programme manager, I want to view Visitation by CDD (Community Drug Distributor) for MDA so that I can monitor CDD-level field activity and coverage during the Mass Drug Administration exercise. | With "Q86. Did someone visit your home between 21st November 2025 and 27th November 2025 to offer your child or children any drug from a bottle?" as the legend and count of "Q86. Did someone visit your home between 21st November 2025 and 27th November 2025 to offer your child or children any drug from a bottle?" under values | • Groups records by CDD.• Displays households/communities visited per CDD.• Updates dynamically with filters. | 5 | High | Faiza Mukhtar | Not Started
Completion
COMP-01 | LGA Planned vs Reached | As a programme manager, I want to compare Planned vs Reached LGAs so that I can track geographic implementation progress against target. | LGA planned on the X-axis and then | • Compares uploaded target/planned LGA list against reached LGAs from submissions.• Displays planned count, reached count, and completion percentage.• Updates dynamically with filters. | 5 | High | Faiza Mukhtar | Not Started
COMP-02 | Settlement Completion Table | As a programme manager, I want a Settlement Completion Table so that I can monitor which settlements have reached their planned household target. |  | • Compares actual submissions per settlement against uploaded target file.• Displays settlement name, planned target, actual reached, and completion status/percentage.• Sortable and filterable table. | 8 | High | Faiza Mukhtar | Not Started
GIS Analysis
GIS-01 | Stacked GPS Point Detection | As a data analyst, I want stacked GPS points identified so that households recorded at the exact same or near-identical location can be investigated. |  | • Detects multiple households sharing identical or near-identical GPS coordinates.• Flags affected records.• Included in validation summary. | 8 | High | Faiza Mukhtar | Not Started
GIS-02 | Mock GPS Detection | As a data analyst, I want records with Mock GPS locations identified so that fabricated or spoofed location data can be flagged for investigation. |  | • Flags records where mock location/GPS spoofing is detected.• Included in validation summary.• Affected records listed. | 5 | High | Faiza Mukhtar | Not Started
GIS-03 | Geolocation Outside LGA Detection | As a GIS analyst, I want survey locations validated against LGA boundaries so that records captured outside their assigned LGA are identified. |  | • Performs spatial join with LGA boundaries.• Flags records outside assigned LGA.• Displays validation status. | 13 | Medium | Faiza Mukhtar | Not Started
GIS-04 | Geolocation Outside Ward Detection | As a GIS analyst, I want survey locations validated against Ward boundaries so that records captured outside their assigned Ward are identified. |  | • Performs spatial join with Ward boundaries.• Flags records outside assigned Ward.• Displays validation status. | 13 | Medium | Faiza Mukhtar | Not Started
Data Quality Checks
DQ-01 | Duplicate Household Detection | As a data analyst, I want duplicate Household records identified so that duplicate interviews can be removed from the coverage survey. | Duplicated HouseHead = VAR Duplicates = FILTER( ADDCOLUMNS( SUMMARIZE('Coverage', 'Coverage'[unique_code]), "CountPerUUID", CALCULATE(COUNTROWS('Coverage')) ), [CountPerUUID] > 1 ) VAR Total = COUNTROWS(Duplicates) RETURN IF(ISBLANK(Total), 0, Total) | • Detects duplicate Household Codes/IDs.• Retains the most recent submission.• Flags superseded records. | 5 | High | Faiza Mukhtar | Not Started
DQ-02 | Repeated Child Selection Check | As a data analyst, I want the system to detect when the same child is selected twice within the same household so that duplicate child selections are identified. | Double Child selection = SUMX( FILTER( ADDCOLUMNS( SUMMARIZE( 'Child Eligible', 'Child Eligible'[Q88. Child name and age ${child_idd} as at when MDA was done (15th to 20th December 2025)] ), "EntryCount", CALCULATE(COUNTROWS('Child Eligible')) ), [EntryCount] > 1 ), [EntryCount] - 1 ) | • Compares child identifiers within the same household.• Flags records where a child appears more than once.• Included in validation summary. | 5 | High | Faiza Mukhtar | Not Started
DQ-03 | Active Research Assistants Tracking | As a programme manager, I want to view the number of Active Research Assistants so that I can monitor which field staff are currently submitting data. | Unique count of "confirm user and phone number" | • Counts unique Research Assistants with submissions within the selected period.• Updates dynamically with filters.• Displayed as KPI card/table. | 3 | High | Faiza Mukhtar | Not Started
DQ-04 | Ineligible Child in Household Detection | As a data analyst, I want children outside the eligible age range flagged so that ineligible child selections can be identified and corrected. | No Eligible Children per HH = COALESCE( COUNTROWS( FILTER( SUMMARIZE( 'Child All Age', 'Child All Age'[_submission__uuid], "EligibleCount", CALCULATE( COUNTROWS('Child All Age'), 'Child All Age'[is_eligible] = 1 ) ), [EligibleCount] = 0 ) ), 0 ) | • Flags children selected outside the eligibility age range (1-59 months).• Included in validation summary.• Affected records listed. | 3 | High | Faiza Mukhtar | Not Started
DQ-05 | Duplicate Child Detection | As a data analyst, I want duplicate child records identified across the dataset so that duplicate child entries can be removed. | Duplicated Child = VAR CHDuplicates = FILTER( ADDCOLUMNS( SUMMARIZE('Child Eligible', 'Child Eligible'[unique_code2]), "CountPerUUID", CALCULATE(COUNTROWS('Child Eligible')) ), [CountPerUUID] > 1 ) VAR Total = COUNTROWS(CHDuplicates) RETURN IF(ISBLANK(Total), 0, Total) | • Detects duplicate child identifiers.• Retains the most recent submission.• Flags superseded records. | 5 | High | Faiza Mukhtar | Not Started
DQ-06 | Settlement Type Mismatch Detection | As a data analyst, I want households flagged where the wealth index does not match the recorded settlement type so that inconsistent settlement classification can be reviewed. | Settlement Type Mismatch = COALESCE( COUNTROWS( FILTER( Coverage, VAR IsUrban = Coverage[Q5. Type of Settlement] = "Urban" VAR IsRural = Coverage[Q5. Type of Settlement] = "Rural" VAR YesCount = (Coverage[Q23. Electricity] = "Yes") + (Coverage[Q24. Radio] = "Yes") + (Coverage[Q25. Television] = "Yes") + (Coverage[Q26. A non-mobile telephone] = "Yes") + (Coverage[Q27. Computer] = "Yes") + (Coverage[Q28. Refrigerator] = "Yes") + (Coverage[Q29. Chair] = "Yes") + (Coverage[Q30. Bed] = "Yes") + (Coverage[Q31. Sofa] = "Yes") + (Coverage[Q32. Cupboard] = "Yes") VAR NoCount = (Coverage[Q23. Electricity] = "No") + (Coverage[Q24. Radio] = "No") + (Coverage[Q25. Television] = "No") + (Coverage[Q26. A non-mobile telephone] = "No") + (Coverage[Q27. Computer] = "No") + (Coverage[Q28. Refrigerator] = "No") + (Coverage[Q29. Chair] = "No") + (Coverage[Q30. Bed] = "No") + (Coverage[Q31. Sofa] = "No") + (Coverage[Q32. Cupboard] = "No") RETURN (IsUrban && NoCount = 10) ¦¦ (IsRural && YesCount = 10) ) ), 0 ) | • Compares wealth index against settlement type.• Flags mismatched records.• Included in validation summary. | 5 | High | Faiza Mukhtar | Not Started
DQ-07 | Form Validation Status | As a data analyst, I want to view the overall Form Validation Status so that I know which submissions have passed or failed validation checks. |  | • Displays validation status (Valid/Flagged) per record.• Updates dynamically after validation checks run.• Displayed as KPI/table. | 3 | High | Faiza Mukhtar | Not Started
DQ-08 | Error Summary by LGA | As a programme manager, I want an Error Summary by LGA so that I can see which LGAs have the highest number of validation errors. |  | • Groups flagged records by LGA.• Displays count and percentage of errors per LGA.• Sortable by count or percentage. | 5 | High | Faiza Mukhtar | Not Started
DQ-09 | Error Log by Research Assistant | As a programme manager, I want a detailed Error Log by Research Assistant so that I can review specific validation failures per field staff member. | This should be a table, with the following columns "Q2. Local Government Area", "Q3.Ward", "Q4. Community Name", unique names for "confirm user and phone number" column for research assistant information, "unique_code" for the Household Code, "Settlement Type Mismatch = COALESCE( COUNTROWS( FILTER( Coverage, VAR IsUrban = Coverage[Q5. Type of Settlement] = "Urban" VAR IsRural = Coverage[Q5. Type of Settlement] = "Rural" VAR YesCount = (Coverage[Q23. Electricity] = "Yes") + (Coverage[Q24. Radio] = "Yes") + (Coverage[Q25. Television] = "Yes") + (Coverage[Q26. A non-mobile telephone] = "Yes") + (Coverage[Q27. Computer] = "Yes") + (Coverage[Q28. Refrigerator] = "Yes") + (Coverage[Q29. Chair] = "Yes") + (Coverage[Q30. Bed] = "Yes") + (Coverage[Q31. Sofa] = "Yes") + (Coverage[Q32. Cupboard] = "Yes") VAR NoCount = (Coverage[Q23. Electricity] = "No") + (Coverage[Q24. Radio] = "No") + (Coverage[Q25. Television] = "No") + (Coverage[Q26. A non-mobile telephone] = "No") + (Coverage[Q27. Computer] = "No") + (Coverage[Q28. Refrigerator] = "No") + (Coverage[Q29. Chair] = "No") + (Coverage[Q30. Bed] = "No") + (Coverage[Q31. Sofa] = "No") + (Coverage[Q32. Cupboard] = "No") RETURN (IsUrban && NoCount = 10) ¦¦ (IsRural && YesCount = 10) ) ), 0 )" for settlement type mismatch, "Q5. Type of Settlement" for the type os settlement column, "Duplicated HouseHead = VAR Duplicates = FILTER( ADDCOLUMNS( SUMMARIZE('Coverage', 'Coverage'[unique_code]), "CountPerUUID", CALCULATE(COUNTROWS('Coverage')) ), [CountPerUUID] > 1 ) VAR Total = COUNTROWS(Duplicates) RETURN IF(ISBLANK(Total), 0, Total)" for duplicated household column, "Duplicated Child = VAR CHDuplicates = FILTER( ADDCOLUMNS( SUMMARIZE('Child Eligible', 'Child Eligible'[unique_code2]), "CountPerUUID", CALCULATE(COUNTROWS('Child Eligible')) ), [CountPerUUID] > 1 ) VAR Total = COUNTROWS(CHDuplicates) RETURN IF(ISBLANK(Total), 0, Total)" for the duplicated child column, "Mock_GPS_ = COALESCE( CALCULATE ( COUNTROWS ( 'Coverage' ), FILTER ( 'Coverage', NOT ISBLANK('Coverage'[_Q9. GPS coordinates_precision]) && 'Coverage'[_Q9. GPS coordinates_precision] < 2 ) ), 0 )" for the Mock GPS column, "Stacked Point_ = VAR DuplicateRows = CALCULATETABLE( 'Coverage', FILTER( 'Coverage', NOT ISBLANK('Coverage'[_Q9. GPS coordinates_latitude]) && NOT ISBLANK('Coverage'[_Q9. GPS coordinates_longitude]) && CALCULATE( COUNTROWS('Coverage'), ALLEXCEPT( 'Coverage', 'Coverage'[_Q9. GPS coordinates_latitude], 'Coverage'[_Q9. GPS coordinates_longitude] ) ) > 1 ) ) RETURN IF( ISBLANK(COUNTROWS(DuplicateRows)), 0, COUNTROWS(DuplicateRows) )" for the stacked point column | • Displays LGA, Ward, Community, Research Assistant and Household Code per record.• Displays Settlement Type Mismatch, Type of Settlement, Duplicated Household, Duplicated Child, Mock GPS and Stacked Point flags.• Filterable and sortable table. | 8 | High | Faiza Mukhtar | Not Started
Validation
VAL-01 | Education vs Occupation Consistency Check | As a validator, I want to compare the Household Head's Education level against the Occupation listed so that inconsistent responses can be flagged for review. |  | • Compares education field against occupation field for logical consistency.• Flags records where the combination is implausible.• Displayed as a validation column on the dashboard. | 5 | High | Faiza Mukhtar | Not Started
VAL-02 | Repetitive Child Selection per Household | As a validator, I want to see when a child has been selected more than once within the same household so that duplicate child selections can be reviewed and corrected. |  | • Flags households with more than one identical child selection.• Displayed as a validation column on the dashboard.• Available for validator review. | 5 | High | Faiza Mukhtar | Not Started
VAL-03 | Gender vs Name Consistency Check | As a validator, I want to see when a respondent's recorded gender does not correlate with their name so that potential data entry errors can be flagged for review. |  | • Cross-references recorded name against recorded gender using a name-gender reference list.• Flags mismatched records.• Displayed as a validation column on the dashboard. | 8 | High | Faiza Mukhtar | Not Started
VAL-04 | Child Name vs Vaccination Card Check | As a validator, I want to compare the child's recorded name against the name on the vaccination card, where available, so that mismatches can be flagged for review. |  | • Compares recorded child name to vaccination card name where a card is available.• Flags mismatched or missing records.• Displayed as a validation column on the dashboard. | 5 | High | Faiza Mukhtar | Not Started
VAL-05 | Household ID Duplicate Flag | As a validator, I want household ID duplicates flagged so that repeated household records can be reviewed and resolved. |  | • Detects duplicate Household IDs.• Flags all occurrences for validator review.• Displayed as a validation column on the dashboard. | 5 | High | Faiza Mukhtar | Not Started
VAL-06 | Non-Eligible Children Flag | As a validator, I want records with non-eligible children flagged so that children outside the eligible age range can be reviewed and corrected. |  | • Flags children outside the 1-59 month eligibility window.• Displayed as a validation column on the dashboard.• Available for validator review. | 3 | High | Faiza Mukhtar | Not Started